## OEMS- SMS
Module | Feature | Sub Fetaures | Test Case ID | Test Case Description | Test Type | Expected Result | Actual Result | Status | Test Date | Tester | Comment
SMS | Dynamic SMS | Send Dynamic Sms | dymc_62 | Verify that all the controls,web elements, design, responsiveness, font and colour is accroding to the UI requirement | UI | All the UI requirements should be covered | All the UI requirements arenot covered | Passed | 2023-03-21 | Tester | " : " symbol is missing in text feilds
SMS | Dynamic SMS | Send Dynamic Sms | dymc_63 | Verify that All mandatory fields should be validated and indicated by an asterisk (*) symbol in the required fields | Validation | must be showing asterisk symbol in the required fields | showing * symbol in the required fields | Passed | 2023-03-22 | Tester
SMS | Dynamic SMS | Send Dynamic Sms | dymc_64 | Verify that all the text fields are default when page is appear. | Validation | test fields should show default | text fields are showing default | Passed | 2023-03-23 | Tester
SMS | Dynamic SMS | Send Dynamic Sms | dymc_65 | Check that Drop-down text field values should be displayed in the list order | Functional | values should be showing in the list order | values are showing in the list order | Passed | 2023-03-24 | Tester
SMS | Dynamic SMS | Send Dynamic Sms | dymc_66 | Check once dropdown is selected, you should be able to select values by keyboard arrow keys or mouse scroll even if dropdown is closed. | Functional | must be able to select value | selects value | Passed | 2023-03-25 | Tester
SMS | Dynamic SMS | Send Dynamic Sms | dymc_67 | Verify that required fields is empty and clicked next button that has show alert message in the required field | Validation | should be showing alert message | Alert message is successfully showing | Passed | 2023-03-26 | Tester
SMS | Dynamic SMS | Send Dynamic Sms | dymc_68 | check when all the required fileds is filled up and clicked next button, that appear correct navigation page | Functional | must be going to the correct navigation page | going to the correct navigation page | Passed | 2023-03-27 | Tester
SMS | Dynamic SMS | Send Dynamic Sms | dymc_69 | check that new naigation page all the controls,web elements, design, responsiveness, font and colour is accroding to the UI requirement | UI | All the UI requirements should be covered | All the UI requirements are covered | Passed | 2023-03-28 | Tester
SMS | Dynamic SMS | Send Dynamic Sms | dymc_70 | Verify that all the text fields are default when page appear. | Validation | text fields should be default | text fields is showing default | Passed | 2023-03-29 | Tester
SMS | Dynamic SMS | Send Dynamic Sms | dymc_71 | verify that pop up window will appear when all the fields are filled up and clicked load & preview data | Functional | pop up window must appear | pop up window successfully appear | Passed | 2023-03-30 | Tester
SMS | Dynamic SMS | Send Dynamic Sms | dymc_72 | Verify that Search results displayed should be relevant to search keyword | Functional | Search results displayed should be relevant to search keyword | Search results displayed are relevant to search keyword | Passed | 2023-03-31 | Tester
SMS | Dynamic SMS | Send Dynamic Sms | dymc_73 | Verify that When user start typing word in text box it should suggest that matches typed keyword | Functional | Must suggest that matches the typed keyword | suggests that matches the typed keyword | Passed | 2023-04-01 | Tester
SMS | Dynamic SMS | Send Dynamic Sms | dymc_74 | check when select a particular student and click next button, new navigation page will appear | Functional | should be going to new navigation page | going to the new navigation page | Passed | 2023-04-02 | Tester
SMS | Dynamic SMS | Send Dynamic Sms | dymc_75 | check it new navigation page data is shown correct or not | Functional | correct data should be showing in the page | shows correct data | Passed | 2023-04-03 | Tester
SMS | Dynamic SMS | Send Dynamic Sms | dymc_76 | check if success popup message is showing when clicked send button in the page | Validation | must be showing popup success message | showing popup success message | Passed | 2023-04-04 | Tester